## Sheet1
Product Backlog
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Molecular Structure Visualization | Visualization | As a researcher, I want to visualize molecular structures in 2D/3D so that I can analyze chemical properties. | Must Have | Completed | Users can load and interact with molecular models in real-time. | 3D model rendering, molecular interaction tools. | Fast rendering, cross-platform support. | 5 | 2
2 | SMILES Notation Parser | Molecule Generation | As a developer, I want to input SMILES notation and generate a molecular structure so that I can create custom molecules. | Must Have | Completed | SMILES input correctly converts to 3D molecular models. | SMILES parser, error handling, molecule validation. | High accuracy, error tolerance. | 4 | 3
3 | AI-Powered Molecule Generation | AI & ML | As a scientist, I want to generate new molecules based on AI predictions so that I can explore potential drug candidates. | Must Have | Completed | AI model successfully generates novel molecules with valid properties. | Graph Neural Networks for molecule generation. | Efficient model inference, cloud scalability. | 7 | 6
4 | Real-Time Collaboration | Collaboration | As a research team, we want to collaborate in real-time on molecular structures so that we can improve research efficiency. | Must Have | Completed | Multiple users can edit and comment on molecules simultaneously. | Live editing, version control, user roles. | Low-latency updates, data synchronization. | 6 | 2
5 | Group Messaging & Annotations | Collaboration | As a user, I want to chat and annotate molecular structures so that I can communicate with my team effectively. | Should Have | Completed | Users can send messages and leave annotations on molecular models. | Chat system, annotation overlay, notifications. | Secure, real-time messaging. | 5 | 1
6 | Molecular Property Prediction | AI & ML | As a researcher, I want to predict molecular properties like solubility and toxicity so that I can assess potential applications. | Should Have | Completed | ML models provide accurate predictions on molecular properties. | Pre-trained models for property prediction. | Accurate, explainable AI predictions. | 6 | 7
7 | Secure Data Storage | Infrastructure | As a user, I want my molecular data securely stored so that I can access my research anytime. | Must Have | Completed | Data is encrypted and stored securely in the cloud. | Cloud storage, encryption, user authentication. | GDPR compliance, high availability. | 4 | 4
8 | API for External Data Integration | Interoperability | As a developer, I want to integrate external molecular databases so that I can use existing research data. | Could Have | Completed | Supports integration with PubChem, ChEMBL, and PDB. | REST API, database connectors, OAuth. | Fast API response times. | 5 | 2
9 | User Authentication & Role Management | Security | As an admin, I want to manage user roles and permissions so that I can control data access. | Must Have | Completed | Users can sign up, log in, and have assigned roles. | OAuth, JWT authentication, admin panel. | Secure authentication, encrypted user data. | 3 | 1
10 | Export & Report Generation | Reporting | As a researcher, I want to export molecular data and reports so that I can document my findings. | Should Have | Completed | Users can export reports in PDF, CSV, and JSON formats. | Report generation module, export options. | Fast processing, downloadable formats. | 4 | 2
11 | Search & Filter Molecules | Usability | As a user, I want to search and filter molecules so that I can quickly find specific structures. | Must Have | Completed | Users can search by name, SMILES, or properties. | Full-text search, category filters, sorting options. | Fast retrieval, optimized indexing. | 4 | 2
12 | Version Control for Molecules | Collaboration | As a researcher, I want to track changes to molecular structures so that I can revert to previous versions. | Should Have | Completed | Users can view and restore previous versions of molecules. | Versioning system, undo/redo functionality. | Efficient storage of multiple versions. | 5 | 6
13 | AI-Powered Reaction Prediction | AI & ML | As a chemist, I want to predict reactions between molecules so that I can explore synthesis pathways. | Could Have | Completed | AI models suggest reaction mechanisms and potential products. | Transformer-based reaction prediction. | High accuracy, fast inference. | 7 | 7
14 | Customizable Dashboards | Usability | As a user, I want a customizable dashboard so that I can tailor the interface to my workflow. | Could Have | Completed | Users can configure widgets and data views. | Dashboard builder, drag-and-drop UI. | Responsive design, persistent user settings. | 3 | 4
15 | Mobile-Friendly Interface | Accessibility | As a researcher, I want a mobile-friendly UI so that I can access molecular data on the go. | Should Have | Completed | Platform works on mobile devices with responsive design. | Adaptive UI, touch-friendly controls. | Fast loading, optimized for mobile browsers. | 5 | 2